## Sheet1
	Week 1	Week 2	Week 3	Week 4	Week 5	Week 6	Week 7	Week 8
Features	06/08/15	06/15/15	06/22/15	06/29/15	07/06/15	07/13/15	07/20/15	07/27/15
Signup/Register	DONE
Login w/Social Media	DONE
Sync Contacts				X
Invite Contacts				X
Add/Remove Sports	DONE
Search People & Services	DONE
Map Search Results	DONE
Add/Remove Person for Remembered	DONE
Find Venues	DONE
Add/Remove Venues for Remembered	DONE
Book Services (Book'em interface)
Add Spot	X
Add Review for Spot	X	X
Messages
Profile – manage info	DONE
Profile – subscriptions			X
Profile – public view	DONE
Settings – push notifications				X
Settings – email notifications			X
Settings – geolocation settings			X
Search Friends on Social Networks				X
Invite friends from Social Networks					X
Share venue/services with Social Networks					X
Phone Checkins					X
Phone UI for website services				X
Deploy App	DONE

Admin Panel for Staff
Dashboard						X
Reports						X
Messages							X
Approve Venues							X
Manage Reviews							X
Manage Subscriptions								X
Manage Users								X